## Executive Dashboard
Duckworks AIMS Management Review Dashboard
v1.5 ¦ synthetic management-system cycle ¦ review date 2026-09-08; gate scenario as of 2026-10-01
AIMS risks | Critical | High | Moderate | Opportunities | Objectives met | At risk | Blocked
7 | 1 | 5 | 1 | 1 | 3 | 3 | 2
Actions | Overdue escalation | Blocked dependency | Open monitoring | Auto-closed | Human decision required
6 | 1 | 1 | 4 | 0 | Yes
Management decision | Basis | Assigned response | Evidence boundary
Retain current system gates | No new production-effectiveness or closure evidence | Do not change system risk scores or lifecycle gates | Synthetic review; no risk acceptance
Escalate AIMS-ACT-003 | Competence action is overdue in the gate scenario | Human owner to reassess and record disposition | Script cannot authorize or close
Maintain PondGPT restriction | Five supplier conditions remain unresolved | Track AIMS-ACT-002 as blocked dependency | No broader-rollout approval
Prioritize operating evidence | Only 3 of 6 registered systems have worked evidence | Execute AIMS-ACT-004 and AIMS-ACT-006 | No production effectiveness claim
Risk | Current score
AR-01 | 12
AR-02 | 8
AR-03 | 15
AR-04 | 15
AR-05 | 12
AR-06 | 15
AR-07 | 20
Boundary: all inputs, review outcomes and gate results are synthetic portfolio evidence. They do not establish production operation, ISO/IEC 42001 conformity, certification, legal compliance, independent assurance or validated risk reduction.

## Risks & Opportunities
AIMS Risk and Opportunity Register
Eight management-system records ¦ scoring is portfolio prioritization, not ISO conformity or enterprise risk acceptance
Entry_ID | Type | Cause | Event_or_Opportunity | Consequence_or_Value | Inherent_Likelihood_or_Feasibility | Inherent_Impact_or_Value | Inherent_Score | Existing_Response | Current_Likelihood_or_Feasibility | Current_Impact_or_Value | Current_Score | Rating_or_Priority | Treatment_or_Enablement | Owner | Due_Date | Status | Linked_Objectives | Evidence_ID | Review_Trigger | Boundary
AR-01 | Risk | Normative requirements and exact applicability references are not yet verified | The AIMS control and evidence map may omit or misstate a requirement | Misaligned assurance claims or incomplete readiness decisions | 4 | 4 | 16 | Thematic baseline and explicit limitation | 3 | 4 | 12 | High | Verify requirement-level and Annex A mapping against an authorized standard and second-person review | Eleanor Duckford - AI Governance Lead | 2026-10-30 | Open | OBJ-08 | EV-AIMS-010 | Authorized standard review or mapping change | Thematic portfolio mapping only; no conformity claim
AR-02 | Risk | Multiple formats and versions can diverge | A decision may rely on a stale or non-authoritative artifact | Reduced traceability and unreliable evidence retrieval | 4 | 4 | 16 | v1.4 document-control standard and priority register | 2 | 4 | 8 | Moderate | Extend authority, retrieval and supersession testing across the repository | Eleanor Duckford - AI Governance Lead | 2026-11-15 | In Progress | OBJ-04;OBJ-05;OBJ-08 | EV-AIMS-010 | New version, broken link or retrieval failure | Priority-scope synthetic control; enterprise operation unverified
AR-03 | Risk | Only one of three synthetic competence records is eligible | A controlled activity may be performed without current competence evidence | Invalid authorization or ineffective human oversight | 4 | 5 | 20 | Competence standard, register and executable gate | 3 | 5 | 15 | High | Remediate expired refresher and below-threshold assessment; require human renewal | Relevant Business Owners | 2026-09-30 | In Progress | OBJ-06 | EV-AIMS-010 | Expiry, failed assessment, role change or requested authorization | No real personnel competence or authorization claim
AR-04 | Risk | Five PondGPT broader-rollout supplier conditions remain open | Supplier change or missing evidence may exceed the restricted-pilot boundary | Security, privacy, continuity and exit exposure | 4 | 5 | 20 | Conditional supplier gate and restricted pilot | 3 | 5 | 15 | High | Obtain verified evidence and executed terms; retain sensitive-source and broader-rollout blocks | Percival Duckworth - Director Procurement & Vendor Assurance | 2026-12-15 | Blocked | OBJ-03 | EV-AIMS-010 | Supplier evidence, change, renewal, incident or expansion request | Fictional supplier; no executed terms or operating history
AR-05 | Risk | One AIMS-wide review is demonstrated only as a bounded exercise | Management review may not recur or drive timely follow-up | Stale objectives, unresolved actions and weak accountability | 4 | 4 | 16 | Static decision brief and MR-AIMS-2026-002 exercise | 3 | 4 | 12 | High | Approve quarterly cadence, required inputs, secretariat and follow-up evidence | Reginald Duckman - CRCO | 2026-10-15 | Open | OBJ-04;OBJ-05 | EV-AIMS-010 | Missed review date or material AIMS change | One synthetic review does not prove recurring operation
AR-06 | Risk | No independent enterprise AIMS audit program is operating | Material governance weaknesses may remain unchallenged | False confidence and delayed corrective action | 4 | 5 | 20 | One bounded DuckTalent finding-to-closure cycle | 3 | 5 | 15 | High | Establish risk-based AIMS internal-audit program with independence safeguards | Head of Internal Audit | 2026-11-30 | Open | OBJ-07 | EV-AIMS-010 | Audit plan approval, significant finding or independence conflict | Portfolio self-assessment is not independent assurance
AR-07 | Risk | Defined-period production effectiveness evidence is absent | Synthetic control results may be mistaken for sustained production performance | Unsupported risk reduction or deployment decisions | 5 | 5 | 25 | Evidence-state rules and six explicit unavailable records | 4 | 5 | 20 | Critical | Obtain version-bound FeatherForecast production monitoring, exceptions and review evidence | Dr. Ada Duckfield - Head of Data & AI | 2026-12-31 | Open | OBJ-02;OBJ-05 | EV-AIMS-010 | Production evidence receipt, material change or gate decision | No production operation or validated effectiveness claim
AO-01 | Opportunity | Three registered systems lack worked evidence chains | Extend bounded evidence architecture to AI-001, AI-002 and AI-003 | Improve portfolio coverage from three of six to six of six systems | 4 | 4 | 16 | Reusable evidence-card and executable-control patterns exist | 4 | 4 | 16 | High priority | Create focused evidence packages only where they add distinct control archetypes | Eleanor Duckford - AI Governance Lead | 2026-12-31 | Open | OBJ-01 | EV-AIMS-010 | Portfolio prioritization or evidence-package completion | Portfolio value opportunity; not production risk reduction

## Objectives P2
AIMS Objectives — Period 2 Snapshot
Release-triggered reconciliation ¦ OBJ-04 and OBJ-05 updated for 58 canonical evidence records
Objective_ID | Objective | Prior_Current_Numerator | Prior_Current_Denominator | Current_Numerator | Current_Denominator | Target_Rate | Prior_Status | Current_Status | Change_Explanation | Management_Response | Owner | Evidence_ID | Boundary
OBJ-01 | Evidence-backed lifecycle decision coverage for registered AI systems | 3 | 6 | 3 | 6 | 1.0 | At risk | At risk | No new system evidence package in v1.5 | Retain targeted coverage action for AI-001, AI-002 and AI-003 | Eleanor Duckford - AI Governance Lead | EV-AIMS-011 | Synthetic coverage does not prove production effectiveness
OBJ-02 | Production AI systems with defined-period production effectiveness evidence | 0 | 1 | 0 | 1 | 1.0 | At risk | At risk | No production evidence added | Obtain FeatherForecast version-bound monitoring and exception evidence | Dr. Ada Duckfield - Head of Data & AI | EV-AIMS-011 | No production effectiveness claim
OBJ-03 | PondGPT broader-rollout supplier conditions closed and independently accepted | 0 | 5 | 0 | 5 | 1.0 | Blocked | Blocked | Five supplier conditions remain open | Maintain restricted pilot and broader-rollout block | Percival Duckworth - Director Procurement & Vendor Assurance | EV-AIMS-011 | No supplier approval or executed-control claim
OBJ-04 | Canonical evidence records with explicit state and boundary | 50 | 50 | 58 | 58 | 1.0 | Met | Met | Eight management-review-cycle evidence records added | Maintain unique IDs and explicit evidence boundaries | Eleanor Duckford - AI Governance Lead | EV-AIMS-011 | Completeness of index does not validate evidence effectiveness
OBJ-05 | Canonical evidence records available and retrievable | 44 | 50 | 52 | 58 | 0.95 | At risk | At risk | Available evidence increased but six production records remain unavailable | Prioritize production evidence while retaining unavailable records | Eleanor Duckford - AI Governance Lead | EV-AIMS-011 | Availability does not establish adequacy or effectiveness
OBJ-06 | Competence records eligible for human authorization | 1 | 3 | 1 | 3 | 1.0 | Blocked | Blocked | Expired and below-threshold cases remain unresolved | Complete refresher and reassessment before human renewal | Relevant Business Owners | EV-AIMS-011 | Eligibility does not grant authorization
OBJ-07 | Bounded audit CAPA cycles meeting stated closure criteria | 1 | 1 | 1 | 1 | 1.0 | Met | Met | No new CAPA; prior bounded closure remains valid | Retain reopening triggers and build enterprise audit cadence | Head of Internal Audit | EV-AIMS-011 | One synthetic closure is not an independent audit program
OBJ-08 | Priority management-system documents under explicit control | 14 | 14 | 22 | 22 | 1.0 | Met | Met | Eight v1.5 canonical artifacts added to priority control scope | Update register after publication and test retrieval | Eleanor Duckford - AI Governance Lead | EV-AIMS-011 | Priority scope is not a complete enterprise records inventory

## Management Actions
AIMS Management Action Tracker
Six assigned actions ¦ status changes require retained evidence and human disposition
Action_ID | Decision_ID | Action | Priority | Owner | Assigned_Date | Due_Date | Status | Dependency | Completion_Evidence | Escalation_Rule | Expected_Gate_Result | Evidence_ID | Boundary
AIMS-ACT-001 | MRD-005 | Verify requirement-level and Annex A mappings against an authorized standard and second-person review | High | Eleanor Duckford - AI Governance Lead | 2026-09-08 | 2026-10-30 | Open | Authorized standard access and competent reviewer | Approved mapping register with review record | Escalate if overdue or mapping is used for a conformity claim | MONITOR_OPEN | EV-AIMS-014 | Thematic mapping remains current until verified
AIMS-ACT-002 | MRD-003 | Close five PondGPT broader-rollout supplier conditions with verified evidence and executed terms | High | Percival Duckworth - Director Procurement & Vendor Assurance | 2026-09-08 | 2026-12-15 | Blocked | Supplier evidence and executed contractual terms | Five condition closures with verification and authorized decision | Keep broader rollout blocked while any dependency or condition remains open | BLOCKED_DEPENDENCY | EV-AIMS-014 | Fictional supplier; no executed terms
AIMS-ACT-003 | MRD-002 | Complete expired refresher and below-threshold reassessment before authorization renewal | High | Relevant Business Owners | 2026-09-08 | 2026-09-30 | In Progress | Training and assessment availability | Current completion records, passing scores and human renewal decisions | Escalate to CRCO on first day overdue; authorization remains blocked | ESCALATE_OVERDUE | EV-AIMS-014 | No real personnel or employment decision
AIMS-ACT-004 | MRD-001 | Obtain version-bound FeatherForecast production monitoring, exception and review evidence | High | Dr. Ada Duckfield - Head of Data & AI | 2026-09-08 | 2026-12-31 | Open | Defined production period and approved data access | Population, period, exceptions, reviewer and outcome evidence | Escalate if a risk reduction or gate change is proposed without evidence | MONITOR_OPEN | EV-AIMS-014 | No production effectiveness currently demonstrated
AIMS-ACT-005 | MRD-004 | Establish a risk-based independent AIMS internal-audit program | High | Head of Internal Audit | 2026-09-08 | 2026-11-30 | Open | Audit capacity and independence safeguards | Approved program, scope, criteria, competence and schedule | Escalate missed approval date or independence conflict | MONITOR_OPEN | EV-AIMS-014 | Portfolio self-review is not independent assurance
AIMS-ACT-006 | MRD-006 | Prioritize differentiated evidence work for AI-001, AI-002 and AI-003 | Moderate | Eleanor Duckford - AI Governance Lead | 2026-09-08 | 2026-12-31 | Open | Portfolio capacity and distinct control archetype | Approved prioritization decision and bounded evidence packages | Defer if work duplicates existing archetypes or weakens consolidation | MONITOR_OPEN | EV-AIMS-014 | Portfolio opportunity only; no production claim

## Gate Results
Executable Management Action Gate Results
undefined ¦ 6/6 expected results met ¦ zero actions auto-closed
Action ID | Status | Gate Result | Expected | Expected Met | Due Date | As-of Date | Escalation | Auto-closed | Boundary
AIMS-ACT-001 | Open | MONITOR_OPEN | MONITOR_OPEN | Yes | 2026-10-30 | 2026-10-01 | No | No | Synthetic scenario; human decision required
AIMS-ACT-002 | Blocked | BLOCKED_DEPENDENCY | BLOCKED_DEPENDENCY | Yes | 2026-12-15 | 2026-10-01 | No | No | Synthetic scenario; human decision required
AIMS-ACT-003 | In Progress | ESCALATE_OVERDUE | ESCALATE_OVERDUE | Yes | 2026-09-30 | 2026-10-01 | Yes | No | Synthetic scenario; human decision required
AIMS-ACT-004 | Open | MONITOR_OPEN | MONITOR_OPEN | Yes | 2026-12-31 | 2026-10-01 | No | No | Synthetic scenario; human decision required
AIMS-ACT-005 | Open | MONITOR_OPEN | MONITOR_OPEN | Yes | 2026-11-30 | 2026-10-01 | No | No | Synthetic scenario; human decision required
AIMS-ACT-006 | Open | MONITOR_OPEN | MONITOR_OPEN | Yes | 2026-12-31 | 2026-10-01 | No | No | Synthetic scenario; human decision required

## Review Inputs
Management Review Input Summary
MR-AIMS-2026-002 ¦ evidence-consuming synthetic review
Input | Observed condition | Decision implication | Evidence IDs
Prior actions | v1.4 support milestone published; objectives and support controls available | Move from design to management use and follow-up | EV-AIMS-001–008
Objectives | 3 Met, 3 At risk, 2 Blocked | Assign actions; retain existing gates | EV-AIMS-011
AIMS risks | 1 Critical, 5 High, 1 Moderate; one High opportunity | Prioritize AR-07, AR-03, AR-04 and AR-06 | EV-AIMS-010
Evidence coverage | 58 records; 52 available; 6 unavailable; 3/6 systems have worked evidence | No production-effectiveness claim | EV-AIMS-011
Supplier governance | PondGPT conditions remain unresolved | Maintain restricted pilot | EV-PT-013; EV-AIMS-010
Competence | One eligible and two blocked synthetic records | Escalate overdue remediation in follow-up scenario | EV-AIMS-004; EV-AIMS-015
Audit/improvement | One bounded audit cycle; no recurring independent program | Create AIMS-ACT-005 | EV-AUD-001–008
Management outcome | Six actions assigned; no score or gate changes | Human owners retain all decisions | EV-AIMS-013–016

## Read Me
Read Me — AIMS Risk, Opportunity and Management Review Register
Purpose | Demonstrate a bounded synthetic AIMS risk/opportunity and management-review follow-up cycle.
Release | v1.5
Review record | MR-AIMS-2026-002
Evidence IDs | EV-AIMS-009 through EV-AIMS-016
Editable inputs | Risk/opportunity records, objective observations and management action data.
Calculated fields | Dashboard counts reference the source sheets; the Python gate independently evaluates action conditions.
Human decision boundary | Automation cannot accept risk, change lifecycle gates, authorize deployment or close actions.
Time boundary | The 2026-10-01 gate is an explicit synthetic follow-up scenario, not a claim that calendar time elapsed.
ISO boundary | M01–M18 are local themes; this is not a clause-level conformity assessment or certification claim.
Production boundary | No production operation, effectiveness, legal compliance or independent assurance is asserted.
Maintenance | Reconcile after material evidence changes and before each management review.